## Tabelle1
Celi App Feature Complete Deadlines | [22 empty] | Colors | [16 empty] | Comments
|  |  |  | Feature to complete: SymptomTracker with needed dependencies. | [21 empty] | Deadline Everyone ¦ Working Phase | [13 empty] | 1 | - | Learn / Get in Touch with React Native
|  |  |  | BaseLevel Components have priority | [21 empty] | Deadline Simeon Bösch ¦ Working phase | [13 empty] | 2 | - | Finished initial Implementation
[26 empty] | Deadline Gehard Stark ¦ Working phase | [13 empty] | 3 | - | Used and Tested by Team Members. Bug Fixed. Ready to use.
|  |  |  | TODO | [21 empty] | Deadline Malena Rauch ¦ Working phase | [13 empty] | 4 | - | Assemble all the built components into one app
|  |  | - | Find or create components. If found, customize for our use. | [21 empty] | Deadline Florian Richter ¦ Working phase | [13 empty] | 5 | - | Presentation Preparation ¦¦ Buffer
|  |  | - | Always document every step in the corresponding changelog (Implementation progress, testing, bugfixing). | [35 empty] | 6 | - | Presentation
[23 empty] | Green day |  |  | UX Meeting
[23 empty] | Red day |  |  | Deadline | [15 empty] | Part Done
[23 empty] | Red text |  |  | Missing Information in Component Document
|  |  | März | [17 empty] | April | [29 empty] | Mai
No. | Component | Dependencies | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
General
1 - a) | Custom Button | - | März 20: 1; März 25: 2; März 30: 3; April 9: General done; April 30: 4; Mai 4: 5; Mai 5: 6
1 - b) | Floating Action Button | 1c) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - c) | Floating Action Button Menu Item | 1g) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - d) | Back Button | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - e) | Text Input Field | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - f) | Image | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - g) | Round Picture Button | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - h) | Time Picker | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - i) | Date Picker | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - j) | Bottom Navigation | 1a) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - k) | Textlabel | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - l) | Context Menu | 1m) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - m) | Context Menu Item | 1a) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - n) | Text Area | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - o) | Notes | 1k), 1n) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - p) | Day Select | 1a), 1k) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - q) | ListItem | 1a), 1g), 1k) | März 20: 1; April 5: 2; April 8: 3; April 30: 4; Mai 4: 5; Mai 5: 6
1 - r) | Round Image | - | März 20: 1; März 25: 2; März 30: 3; April 30: 4; Mai 4: 5; Mai 5: 6
SymptomT.
2 - a) | Symptom Group | 1g), 1k) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - b) | Color Chooser | 1g) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - c) | Add Symptom | 1k), 1e), 1a) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - d) | Search Symptom | 2d i + ii) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - d) - i | Resultlist | 1q) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - d) - ii | Search Bar | 1e), 1a) | März 20: 1; April 15: 2; April 20: 2; April 30: 4; Mai 4: 5; Mai 5: 6
2 - e) | Symptomtracker | 2a-d), 1o), 1p) | März 20: 1; April 23: 2; April 26: 3; April 30: 4; Mai 4: 5; Mai 5: 6
Homescreen
3 - a) | Simple Gluton Implementation | 1f) | März 20: 1; April 15: 2; April 20: 3; April 26: 4; April 30: 4; Mai 4: 5; Mai 5: 6
3 - b) | Swipe Functionality | ? | März 20: 1; April 15: 2; April 20: 3; April 26: 4; April 30: 4; Mai 4: 5; Mai 5: 6
3 - c) | Home Screen | 1j), 1b), 3a/b) | März 20: 1; April 15: 2; April 20: 3; April 26: 4; April 30: 4; Mai 4: 5; Mai 5: 6
Rest of the app will be implemented after the 05.05.2019